## Sheet1
Sr. No. | STEPS to configure recorders from OLAM to SL recording | Start Date | End Date | Status | Comments
10 | Steps required from Stubbing team | 2016-04-13 | 2016-04-18
10.1 | Web--Need to be get updated SL client JAR (from SL dev/Env team) for every release | 2016-04-13 | 2016-04-14 | Done | After confirmation from ENV team, common SL Jar file use for both MOB and Web
10.2 | MOB--Need to be get updated SL client JAR (from SL dev/Env team) for every release |  |  | Done | After confirmation from ENV team, common SL Jar file use for both MOB and Web
10.3 | To extract all class name from this JAR | 2016-04-14 | 2016-04-14 | Done
10.4 | To Validate these class name with our EJB-OLAM Vrs files (for Mob and Web) | 2016-04-14 | 2016-04-14 | Done
10.5 | If any new class found from Jar file the we need to be add in our VRS file or any class is not available in Jar file then we need to be remove from our VRS file | 2016-04-14 | 2016-04-14 | Done
10.6 | Identify the env, where we need to be add our recorders | 2016-04-13 | 2016-04-14 | Done | 4/14:--Sent mail to Gopal and also asked with Env team, OLAM04
10.7 | Need to be setup recording project for particular release | 2016-04-14 | 2016-04-14 | Done
10.8 | Need to be update agent information in Belist under SLSupport folder |  |  | Done
10.9 | Need to be check the status (i.e. start and stop recorders) | 2016-04-18 | 2016-04-18 | Done | This has to be done Before 7 AM CST so offshore will do this activity before recorder start
11 | Steps required from Env team | 2016-04-15 | 2016-04-15
11.1 | Agent configuration On Olam Server (Please refer Wiki--- ) | 2016-04-15 | 2016-04-15 | Done
12 | Testing Steps for recorders working status | 2016-04-18 | 2016-04-18
12.1 | Need to be verify at stub side on Lisa Console | 2016-04-18 | 2016-04-18 | Done
12.2 | For checking the transaction:---check the status of recorders by Raw Tarffic file by using WinScp | 2016-04-18 | 2016-04-18 | Done

## Sheet2
OLAM
SL
BEs
COLDAP
1) Install 2 agents on SL server so that 1 will record SL to BE and other will FE/COLDAP to SL
2) Install only 1 agent on SL server and that will do both recording FE/COLDAP to SL and SL to BE
Note on E9: Author: Olam Agent doing recording of all EJBs from OLAM to SL and vivevasa
Note on G10: Author: SL Agent doing recording of all EJBs from SL to BE and vivevasa
Note on E12: Author: Olam Agent doing recording of all EJBs from COLDAP to SL and vivevasa

## 1608
Sr. No. | STEPS to configure recorders from OLAM to SL recording | Start Date | End Date | Status | Comments
10 | Steps required from Stubbing team
10.1 | Web--Need to be get updated SL client JAR (from SL dev/Env team) for every release | 2016-06-13 | 2016-06-13 | Done | After confirmation from ENV team, common SL Jar file use for both MOB and Web
10.2 | MOB--Need to be get updated SL client JAR (from SL dev/Env team) for every release | 2016-06-13 | 2016-06-13 | Done | After confirmation from ENV team, common SL Jar file use for both MOB and Web
10.3 | To extract all class name from this JAR | 2016-06-13 | 2016-06-13 | Done
10.4 | To Validate these class name with our EJB-OLAM Vrs files (for Mob and Web) | 2016-06-13 | 2016-06-13 | Done
10.5 | If any new class found from Jar file the we need to be add in our VRS file or any class is not available in Jar file then we need to be remove from our VRS file | 2016-06-13 | 2016-06-13 | Done
10.6 | Identify the env, where we need to be add our recorders |  |  | Done | 4/14:--Sent mail to Gopal and also asked with Env team, OLAM04
10.7 | Need to be setup recording project for particular release |  |  | Done
10.8 | Need to be update agent information in Belist under SLSupport folder
10.9 | Need to be check the status (i.e. start and stop recorders) |  |  |  | This has to be done Before 7 AM CST so offshore will do this activity before recorder start
11 | Steps required from Env team
11.1 | Agent configuration On Olam Server (Please refer Wiki--- )
12 | Testing Steps for recorders working status
12.1 | Need to be verify at stub side on Lisa Console
12.2 | For checking the transaction:---check the status of recorders by Raw Tarffic file by using WinScp